## Slide 1
Debre Markos University
Department of Public Health
For post graduate Students
Health service management
By: Nurilign Abebe (Asst Prof of public health)

## Slide 2
Chapter II management functions

## Slide 3
Organizing
Establish task
and authority
relationships that
allow people to work
together to achieve
organization goals.
Planning
Choose appropriate
organizational
goals and courses
of action to best
achieve those goals
Leading
Motivate,
coordinate, and
energize individuals
and groups to work
together to achieve
organizational goals
Controlling
Establish accurate
measuring and
monitoring systems
to evaluate how well
the organization has
achieved its goals.
Four Tasks of Management

## Slide 4: Management functions…
In addition to these, three broad sequential functions (PIE),
Two continuous functions of management are
  Communication &
  Decision- Making.

## Slide 5: What is Planning?
Planning is the process of establishing goals and a suitable course of action for achieving those goals.
Making implementation decision before implementation.
Deciding prospectively what to do charting a course of action for the future

## Slide 6: THE RATIONALE FOR PLANNING
Planning helps :
  Copping with future uncertainty & changes
  Focus attention on objectives
  For economical operation
  Provides performance standards & facilitate control
  Helps foreseeing & identifying potential risks

## Slide 7: FEATURES OF PLANNING
Is an intellectual activity
Is a continuous Process (cyclic /spiral)
Is flexible as it is based on future conditions, which are always dynamic
Must be systematic & action oriented
is collective undertaking requiring the participation of; Professionals ( health & other sectors) , Community/ NGOs and Government bodies
is needed & practiced at all managerial levels regardless of the size (small or complex) & type (non–profit or profit making ) of organization

## Slide 8: What is Planning?...
The important components of this and other similar definitions are concepts of:-
    Where are we going (objectives)
    With what (Resources)
    How (efficient and appropriate implementation)
    When (future)?

## Slide 9: Health Planning (the future and how it will get there)

## Slide 10: What is Health Planning?
Health Planning is the process of defining community health problems, identifying needs and resources, establishing priority goals and setting out the administrative action needed to reach those goals.
Types of planning
Strategic plan
Tactical plan/Operational plan

## Slide 11: Strategic plan
Is plans designed to meet an organizations broad goals.
Is planned for five years or more
Is planned by top level manager
Strategic plan is the process of determining what organization intends to be in future and how it gets there.
Strategic planning is the process of formulating and implementing decisions about an organization’s future direction.

## Slide 12: SWOT Analysis
SWOT (strengths and weakness, opportunities and threats) is a strategic planning tool that matches internal organizational strengths and weakness with external opportunities and threats.
By reviewing strengths, weaknesses, opportunities and threats a useful strategy for achieving objectives will become evident.
In the health sector, strengths may be considered availability of resources and trained human power.
Weaknesses include lack of managerial talent and obsolete facilities. And threats include adverse cultural believes towards modern medical practice and growing cost of essential drugs.
Examples of opportunities are clear and supportive government policies and presence of a functional health committee in the communities.

## Slide 13
Positive | Strengths 1 | Opportunities 3
Negative | Weakness 2 | Threats 4
Internal
External
Figure 1: swot analysis: a frame work for selecting strategies swot matrix

## Slide 14
Positive | Strengths There is policy & guidelines in health Control of communicable disease and epidemics is the top priority of health policy Malaria control programme have been decentralized and integrated into the general health service system of the regions. | Opportunities There is devolution type of decentralization to the regions in line with Federalism There is political will to revitalize multisectoral collaboration and community involvement Non-governmental organization involvement is possible International partners support (WHO)
Negative | Weakness Shortage of drug supply in all health facilities Low coverage of health services over 51% of the population have no access to health services Poor financial allocation for health activities | Threats Poor economic situation Continuity of war High external debt Change of government-change of policy
Example of SWOT analysis :World Health Organization (WHO) Roll Back Malaria (RBM) intervention in Ethiopia

## Slide 15: Tactical plan /Operational plan
Is planned for one year or less
is short-range planning that emphasizes the current operations of various parts of the organization
Is plans developed at the organization’s lower levels that specify action steps toward achieving operational goals

## Slide 16
Major differences between Strategic and Tactical Planning
Area of differences | Strategic Planning | Tactical Planning
Individuals involved | Developed mainly by upper-level management | Developed mainly by lower level management
Facts on which to base planning | Facts are generally difficult to gather | Facts are generally easy to gather
Amount of details in plans | Plans contain relatively little detail | Plans contain substantial amount of detail
Length of time plans cover | Plans cover long periods of time | Plans cover short periods of time

## Slide 17: SCOPE OF PLANNING
What is the target client?
  Population
  Institution
  Program
What the plan intends to address should be clearly defined
What is the target geographical region or area?
  Village/kebele
  District/Zonal
  Region
  At what level you are planning has to be clearly defined

## Slide 18: FEATURES OF PLANING
i. A Good Plan Should Give
  Clear vision/mission, goal and objectives
  A clear picture of the tasks to be accomplished
  A clear picture of resources needed to accomplish the task. In terms of human, material, financial and time resources.
ii. Planning Takes Place at All Levels
  Planning takes place at any level in health system
  Planning takes place continually, it is cyclic process
Planning methods can be applied to :-
  A large programme at national level
  Example –Malaria control programme
  Small one - at village level
  Example –construction of community health post

## Slide 19: FEATURES OF PLANING...
iii. Planning must be Collective
It requires the participation of:-
  Professionals (from health and other sectors)
  Community (NGO)
  Government

## Slide 20: Steps in planning
There are six steps for planning in health activities
  Situational analysis
  Selecting priority problems
  Setting objectives and targets
  Reviewing /Identifying obstacles and limitations
  Designing the strategies
  Prepare the plan

## Slide 21: 1. Situational analysis
Situational analysis is the first step in the development of a plan.
It deals with looking at the whole situation of the community with regard to health and health related problems, analyze the cause of the problems, understanding the community, study the resources and record and tabulate the results.
The purpose of situational analysis is to provide abroad basis of understanding.
This is for two reasons
  It provides a common reference point for the rest of the planning process
  It allows the selection of priority areas of concern for planning content of situational analysis.

## Slide 22: In situational analysis we analyze ….
In situational analysis we analyze
  population characteristics
  policy and political environment
  analyze health needs and health services
  analyze resources
  review past implementation experience

## Slide 23: Sources of information
Formal/official sources – (from records and reports)
Informal sources—(all information which are not from formal sources)
Methods of gathering information
    listening and observing the community
    discussing with the community leaders
    talking with other sectors
    reading health institution records
    referring to survey reports, or census
    conducting baseline survey

## Slide 24: 2. Selecting priority problems
What is problem?
Problem is defined as perceived gap between what is and what should be.
For example, a community might not consider as a problem using open field for reliving one self, but this is a problem for the health worker.
In selecting important problems it is useful to group problems under common headings
For example
Environmental problems
    Poor sanitation, overcrowding, lack of safe drinking water etc
Disease or health problems
  Malaria, Malnutrition, Diarrhea etc Socio economic problems
Health service problems
    Insufficient drugs

## Slide 25: Prioritize the problems
The health worker faces usually with more than one problems at a time and cannot solve them at once. Therefore the important problems selected need to be prioritized.
The following selection criteria are used for priority setting:
  Magnitude of the problem
  Degree of severity
  Feasibility of intervention
  Sustainability of intervention
  Community concern
  Political and social acceptability
  Consistent with multi sectorial approach
  Consistent with government planning
  Clear defined system with donors(if linkage exists)

## Slide 26: 3. Setting objectives and targets
Setting a clear objective is important for two reasons
  It is important for definite plan
  Enables results to be evaluated
Example:
we will improve health (wrong way of setting objectives)
We will extend health care for total population by 2015(right way of setting)

## Slide 27: Characteristics of good objective
Generally, a good objective must be “SMART”
  S specific (put in clear way that addresses a problem)
  M measurable (when the result can be put in numbers)
  A achievable/feasible (possible to achieve)
  R relevant (pertinent to the problem to be solved)
  T time bound (it should have time limit when the desired achievement obtained)

## Slide 28: Setting objectives and targets …
Objectives may be stated in different ways at different level of the health system
For example
at regional level” at the end of five years malnourished children (<3years) will be reduced less than 4%)
At district or woreda level “to identify children of 0-3 years of age with malnutrition according to the stated nutritional criteria.
At kebel/village level “identify among the child population of 0-3 years of age all children with malnutrition, according to the specified criteria.

## Slide 29: 4. Identifying obstacles and limitations
The limitations/obstacles may be
  resources (people, equipment, money etc)
  Environmental (geographical, climate, Technical difficulties , Social factors, etc)
The analysis of obstacles would help the planner to know which
    Obstacle can be removed
    Obstacles can be reduced or modified
    Obstacles cannot removed

## Slide 30: 5. DESIGNING THE STRATEGIES
Once objectives and targets are set, the planner assesses the different ways (strategies) for achieving them.
Choosing the best strategy again entails analysing resources available and needed for each strategy.
The potential strategies often include technology to be applied, procedures to be used and defining the role of communities and other sectors.

## Slide 31: 5. DESIGNING THE STRATEGIES...
For each chosen strategy, the corresponding activities to be undertaken and the resources needed should be detailed,
including who will do the activities (job description of all involved personnel) which things would be needed (equipment, materials and money), where the work will be done and the methods of controlling.

## Slide 32: 6. Writing the plan
The purposes of writing the plan are:-
  To request funds or resources from the government or funding agencies
  For monitoring and evaluating the implementation process by all concerned bodies
Before planning activities it is necessary to:
  Look at different possible ways of achieving the objectives
  Balance resources and needs
  Choose the best action plan then
  Write detailed activities based on the chosen plan of action

## Slide 33: Writing the plan …
A plan can be written in several ways. Some organizations may require plans to be written on specific way.
Some donors or governmental bodies might have a certain guidelines. In the absence of such circumstance, the following headings are helpful to write action plan
  The problem statement
  Objective and targets
  Strategy and activities
  Resources needed and how they are going to be utilized
  Monitoring and evaluation

## Slide 34: Class exercise
Instruction
Be in five a group
Choose one organization
Construct the Mission Statement of an institution.
Construct the Vision Statement of an institution.
Choose one objective and follow planning steps

## Slide 35: Mission and vision statement
Mission
An organization’s mission is:
- its purpose,
- its reason for being,
- provides orientation, consistency, and meaning to the organization’s decisions and activities at all levels.
The Mission Statement describes clearly and concisely why the organization exists.
It should be re-examined periodically by current staff.

## Slide 36
Why does an organization need a Mission?
The Mission is what allows members of an organization to clearly understand why they are doing the work.
Only when health workers are aware of the organizational mission or ultimate purpose, will they fully understand the meaning and the value of their efforts.

## Slide 37: CONSTRUCTING THE MISSION STATEMENT
To construct or revise a Mission Statement, the Board of Directors and Managers and their Teams must carefully scan the internal and external environments before answering four basic questions:
A. What do we do?
B. Whom do we serve?
C. How do we do it? and
D. Why do we do it?
Finalize and disseminate the Mission Statement to staff, and board members, those who are served by the organization, and the general public.

## Slide 38: Identify (what, whom, how and why)
Our mission is to contribute to reducing the number of unwanted pregnancies by providing uninterrupted access to high-quality, modern methods of contraception, through which we can reduce the rate of mortality among reproductive age mothers.

## Slide 39
Where are we going?
- Create a Vision,
You are now ready to take on the challenge of constructing the desired future,
It is the moment to dream, to decide, what your organization wants to be in the future, and
How it wants to be viewed by the outside world.
The vision is like a guiding star.
The vision guides and focuses the organization’s efforts and helps to align, inspire, motivate, and secure the commitment of each working group and individual within the organization.

## Slide 40
CREATING A SHARED VISION
- A vision is more powerful when a large number of people from various organizational levels develop it together than comes from the organization’s upper levels.

## Slide 41
What Experts say about Vision:
According to Karl Albrecht (1994), the vision is the shared image of what we want our organization to be or to become.
For Jay Conger (2000), the vision is a mental image that represents a desirable future state, ideal, or dream with a vast scope.

## Slide 42
CONSTRUCTING THE VISION
STEP-BY-STEP
In constructing the vision, you and your planning team should follow four steps.
Step 1. Keep the big picture in mind. Refer to your organization’s mission and the population you are supposed to serve so that the vision aligns with the mission.

## Slide 43
Step 2. Answer the following questions:
What will our organization look like in three to five years?
What aspects of mission will we have achieved and in what areas will be excel?
What will make us most proud? (e.g. quality of our services, commitment, creativity, financial stability, etc.)
What values do we uphold, and how will they be reflected in our services and the way we run our organization?
Write down the answers to each of the questions and come to consensus within your team.

## Slide 44
Step 3. Look at your organization through the eyes of your target population, beneficiaries, donors, partners, collaborators, competitors, and society in general. For each of these groups, ask:
How do we want these groups to see our organization in three to five years?
What will they say about our services?
What will they say about our staff?
What will they say about our reputation in their communities?
Write down the answers to each of the questions and come to consensus within your team.

## Slide 45
Step 4. Translate these ideas into a few sentences that describe the desired future in the future in a concrete manner;
E.g. Stop Partnership: Our vision is a TB-free world: the first children born this millennium will see TB eliminated in their lifetimes.
TB

## Slide 46: 2. Organizing
Organizing focuses attention on the structure and process of allocating jobs so that common objectives can be achieved.
The most important elements of organization structure are
  Division of labor
  Decentralization
  Delegation and
  Coordination to secure unity
  Authority

## Slide 47: Organization Structure
Section
ORG/Institution
Departments
Division

## Slide 48: 3. Leading/Directing
Leadership is a process of directing and influencing the task-related activities of group members.
The core concepts embedded in leadership are:
  Leadership is a process.
  It manifests itself in the doing; it is a performing art.
  The focus of leadership is in a person.
  The focus of leadership is other individuals and groups.

## Slide 49: Leading/Directing...
  Leadership entails influencing.
  Influence is leadership’s center of gravity and most critical element.
  The objective of leadership is good accomplishment.
  Leadership is instrumental; it is done for a purpose.
  leadership is intentional; it is not accidental.

## Slide 50: Leading/Directing...
Implications:
  Involves other people
  Is unequal distribution of power (leaders/members)
  Is to influence behaviors of employee
  Is about values

## Slide 51: 4. CONTROLLING
Controlling is establish accurate measuring and monitoring systems to evaluate how well the organization has achieved its goals.
Controlling is the measurement and correction of performance in order to ensure the objectives and the plans of the organization are being accomplished.
In other words, controlling is the process by which management sees what did happen.
If the accomplishments are not needed adjustments are made.

## Slide 52: CONTROLLING…
Without systematic control, a manager has no assurance that all elements of the origination will work toward meeting the goals.
Controlling is closely related to planning, organizing & leading.
It helps managers monitor the effectiveness of planning, organizing, leading, and take corrective actions as needed.
It is essentially a managerial function & the establishment of control systems is usually the concept of top and senior managers.
Although, some form of control is needed at all levels of the managerial hierarchy, it is mostly exercised at lower points in the managerial hierarchy.

## Slide 53: CONTROLLING…
Control is not an end in itself rather the primary aim of control is to improve performance by ensuring that resources are more effectively deployed, and that mistakes are rectified.
Therefore, an essential part of the control process is taking corrective actions as needed.

## Slide 54: Pre-requisites of control systems
Controls require plans
  The clearer, more complete and more integrated plans are, the more effective controls can be.
Controls require clear organizational structure
  The clearer, more complete, and more integrated the existences of organizational structure, the more effective control action can be.

## Slide 55: Types of Management Control
There are two types of controls
Organizational controls
E.g. Standards of measurement such as profitability.
Operational controls
E.g. Meeting quality standards during the production process, ensuring enough supply of raw materials.

## Slide 56: Operational controls…
Three types of operational controls:
  1. Predictive controls
  They anticipate problems before they actually occur.
  2.Concurrent controls
  They help us take timely action before large damage takes place.
  3. In Historical controls
  They measure results after the happening of events.

## Slide 57: Components of control
The important components of control are:
    standards
    measurement
    comparison
    appraisal and
    intervention or change

## Slide 58: Steps in the control process
There are essentially four steps in the control process
1.Establishing standards and methods for measuring performance.
The control process begins when standards are set.
Standards are units of measurement established by management to serve as benchmarks for comparing performance levels.

## Slide 59: 1.Establishing standards….
Three different methods are used for establishing standards:
      Judgment
      statistical or historical data &
      observation
A manager arrives at judgmental standards through personal knowledge, experience, and intuition.
For statistical or historical data, past performance is used as a benchmark or goal for future performance.
Workers are observed in action, and standards are set accordingly.

## Slide 60: Types of standards
There are three types of standards
Performance standards - deal with quantity, quality, cost and time.
Corollary standards - support a given level of performance. These include minimum personnel requirements and adequate physical resources.
Standards of conduct - are moral and ethical criteria that shape the behavioural climate of the workplace.
They originate from law, custom, and religious beliefs.

## Slide 61: 2.Measuring Actual Performance
Like all aspects of control, measurement is an ongoing, repetitive process, the frequency of measurement dependant on the type of activity being measured.
Measurement involves comparison between what is accomplished and what was intended to be accomplished. The unit or the gauge thus chosen should be clear, well defined and easily identified, and should be uniform and homogenous through out the measurement process.

## Slide 62: Measuring Actual Performance…
To make sure that any standard, managers measure performance levels accurately and correctly should pay close attention to:
1.Timeliness of Information
Control information is useful only if it is timely.
Managers must have accurate information during each working day so that they have an adequate basis for taking correcting action. To maintain work standards, control measures must be taken at the right time.

## Slide 63: Measuring Actual Performance…
2.Appropriate Units of Measurement
Organizations use several different measurement units to ensure that performance is being gauged adequately. Measures of performance rely on a manager's past experiences and value system.
3.Reliability of Information
Accurate information has consistent data and measures all aspects of the situation.

## Slide 64: Measuring Actual Performance…
4. Validity of Information
Even though information may be reliable, it may be invalid if it does not reflect what it is intended to measure. The best approach to measuring performance is to review all performance.
5. Channeling Information to the proper authority
Control information should be channeled to the person who is accountable for the operation and who has authority to take corrective action.

## Slide 65: Measuring Actual Performance…
6. Simple
Control measures must be simple, otherwise they may take too long to apply and produce the intended effect.
  Minimal
  Controls should be as few as possible, i.e. as few as needed to ensure that the work is done and standards are maintained.
  Flexible
  Controls that are rigid may be self-defeating: staff will try to evade them.

## Slide 66
Establish the standards of performance, goals or targets against which performance is to be evaluated
    Measure actual performance
Compare actual performance against chosen standards
Step 2
Step 1
Step 3
Step 4
Evaluate the result and initiate corrective action if the standard is not being achieved

## Slide 67: Feedback in the Control Process
An essential element in the control process is feedback.
Any feedback system must have a number of characteristics such as:
    Timely
      The information generated by the control process must be fed back in time for remedial action to be taken.
    Reliable
    Precise - should focus on those aspects of performance, which need to be addressed.
    Right – recipient

## Slide 68: Implementation
Implementation
  means translating plan into action.
  Plan is only useful when it ends up in implementable action.
  Without implementation plans remain theoretical
Techniques for improving implementation
1. The health worker(manger) should
    Reviews the plan
    Write detailed activities for each objective
  Make the time table
  Assign responsibility to staffs
  Discus with community how they can participate in the implementation
2. Obtaining the necessary resources on time
    For example securing fund

## Slide 69: Implemen…
3. Involving service managers during the planning process
  Failure to involve them might lead to rejection of the plan or poor performance
  Involving them would create commitment to the plan
4. Documentation
  Recording and maintaining the program activities would help as a checklist for monitoring and evaluation
5. Clear plan for how to use budget for each activity
6. Developing time table for implementation of each activities
      The time table should state when an activity must begin and end, who is responsible and it should include column for remarks.
7. Coordinating the work of the health team
To coordinate work of health team the health worker in charge must:
  Coordinate the members of health team
  Coordinate the activity
  Communicate the decision

## Slide 70: Implemen…
8. Monitoring and redirecting of activities
  Monitoring is the systematic and continual collection, analysis, interpretation and use of data on key aspects of an intervention and/ or its expected results.
  Monitoring is a more frequent activity and usually undertaken at operational level.
8.1. Supervision
  It can be considered as part of monitoring
  It helps to ensure that personnel carry out their activities effectively and become more competent.
There are three main supervision styles;
  Autocratic(do what I say)
  Anarchic(do what you like)
  Democratic(let’s agree on what to do)
The three important things of supervision
  Making supervisory schedule
  Planning supervisory visit
  Conducting supervisory visit

## Slide 71: Implemen…
Poor implementation
  Non implementation of inputs
  Unsuccessful implementation
What is the causes of poor implementation?
  Lack of relevant resources
  poor timing of inputs
  resistance to change
  neglect of institutional or legal requirement
  poor coordination
  poor planning

## Slide 72: Monitoring and evaluating health programs
The importance of monitoring and evaluation
  Monitoring and evaluation are fundamental stages of good quality program management at all levels.(local, regional, national, and international)
  It provides information on the program and its effectiveness
  Improve program management and the decision making process
  Allows for accounting to stakeholders including donors and users of a program
  Provides information for planning future resource demands
  Provides useful information for elaborating policies and for advocacy
Monitoring helps to check
  If activities are completed as planned
  If conducted as scheduled
  If budgets spent as planed
  If any change is needed in management and in implementation
  If work plans need modification
  If work standard is maintained

## Slide 73: Maintaining work standard
A health worker or supervisor must be able to:
  Use checklists to observe performance and identify deficiencies
  Trace the cause of work deficiencies
  Distinguishes whether personal, technical or administrative or organizational reasons attributed to the work deficiencies
  Take corrective actions to maintain the work standard

## Slide 74: Monitoring …
Methods of monitoring
  Continually observing
  Checking supplies against inventories and stock lists
  Examining records and reports
  Discussing with staffs and community
Steps in developing monitoring system
  Define purpose of monitoring
  Design indicators
  Develop monitoring plan
  Develop monitoring format
  Develop data collection and sampling technique
  Design how to organize and analyze
  Plan the system of presentation and how to use the results to improve implementation

## Slide 75: Evaluation
Evaluation is a systematic process of data collection and analysis about activities and/or effects of a program, looking to answer an evaluation questions.
It determines the merit or the value of the program and explains the relationship between the program and its effect.
“Evaluation is not to prove, it is to improve” (Kelloge foundation, 1998)

## Slide 76: Evaluation can be divided as
  summative and formative evaluation
  Or it can be process, outcome and impact evaluation
Evaluation is needed to answer different evaluation questions.
Some of the questions are:
  Was the activity worth(by doing summative evaluation)
  Should the activity be continued(by doing formative evaluation)
  Is the objective achieved?(by doing objective oriented evaluation)
  Should the program adopted elsewhere?(by doing either summative or formative evaluation)

## Slide 77: Evaluation terminology
Input –resources used in the program. They include financial, human and material resources.
Activity—program procedures that are implemented to obtain the desired effect.
Output—are the immediate consequence of the inputs utilized and the program conducted.
Outcomes--- effects upon target population that can lead to the intended ultimate goal of a program. The effects include several types and may focus on awareness, attitude, behavior, utilization, etc.
Impact ---are related to long term accumulative effects of a program. It is rarely attributed to a single program or intervention.
Indicators--Quantitative or qualitative factor or variable that provides a simple and reliable basis for assessing achievement, change or performance